## Sheet1
Item # | Min Time (hrs) | Uncertainty Factor | Max Time (hrs) | Comments | Special Challenges | Hourly Rate | Low Est. | High Est.
2.1 (Brain) | 5 | 2 | 10 |  | Trajectory and velocity projection, error propagation through calculations. Math could get complicated. | 60 | 300 | 600
2.2 (First Aide) | 1 | 1 | 1 | Doesn't do much at this stage since there's no alert system hooked up. To let us know it's working though it should indicate when it would sound an alert. |  | 60 | 60 | 60
2.3 (Sensor) | 2 | 1 | 2 | At this point the sensors read simulated signal strength data from the bot thread. |  | 60 | 120 | 120
2.4 (SDM: Shared Data Manager) | 8 | 1.25 | 10 |  | Concurrency and data sharing across processes over a network is inherently complex. | 60 | 480 | 600
2.5 (Post Office) | 6 | 1.5 | 9 |  | Managing queues and distributing messages can be tricky. | 60 | 360 | 540
2.6 (Bot) | 5 | 1 | 5 | Need to mock up some virtual teams and plays for testing. This might be tedious but won't be very unpredictable. I can do this in a drawing program and export the line data to use as player pathways. |  | 60 | 300 | 300
3 (MPC) | 0.5 | 1 | 0.5 | Initially it's just an NPC that doesn't move and that the tester (you, me, or whomever) interacts with through the GUI or command-line. |  | 60 | 30 | 30
4 (GUI) | 4 | 2 | 8 | Attached to the MPC and gives the tester control over the game and a “god's eye” view of the field. Uncertainty reflects the fact that GUI programming can result in weird glitches with widget sets and event handling. |  | 60 | 240 | 480
Totals | 31.5 |  | 45.5 |  |  |  | 1890 | 2730