## Sheet1
Item # | Min Time (hrs) | Uncertainty Factor | Max Time (hrs) | Comments | Special Challenges | Hourly Rate | Low Est. | High Est.
2.1 (Brain) | 2 | 1 | 2 | Initially there is no preference shown to any other PC but as position information becomes known each PC should assign greater value to data from the PCs near itself. A player is in no danger of colliding with another player at the other end of the field, but a player 10ft away is another matter. This was the most obvious thing that would be nice but isn't needed for Stage 1 to work. There may be other things that come to mind. |  | 60 | 120 | 120
2.2 (First Aide) | 4 | 2 | 8 |  | This component now becomes more complex. We should have real hardware to control here so there may be interfacing with lights or small speakers here. | 60 | 240 | 480
2.3 (Sensor) | 4 | 4 | 16 |  | Here we will be reading from real world sensors, possibly 3 wifi cards at once. As I mentioned in the Stage 1 docs this could get complicated. | 60 | 240 | 960
2.4 (SDM: Shared Data Manager) | 0 | 0 | 0 |  |  | 60 | 0 | 0
2.5 (Post Office) | 0 | 0 | 0 |  |  | 60 | 0 | 0
2.6 (Bot) | 0 | 0 | 0 |  |  | 60 | 0 | 0
3 (MPC) | 0 | 0 | 0 |  |  | 60 | 0 | 0
4 (GUI) | 4 | 1 | 4 | Perhaps Better GUI, more stats and controls displayed. Uncertainty should be less after initial GUI is built, these would just be improvements. |  | 60 | 240 | 240
Totals | 14 |  | 30 |  |  |  | 840 | 1800